## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introductio to project-Stock Singnal System | MUST HAVE | No Dependency | All Team memebers | 3- Completed
S2 | S2 | US-001 | Data Collection-stocks price using API | MUST HAVE | yfinance | Vaishnavi | 3- Completed
S3 | S3 | US-001 | Signal generation | MUST HAVE | RSI/Moving Average | Kranthi | 3- Completed
S4 | S4 | US-001 | Backend development | MUST HAVE | Flask/Python | Pravin and Harshitha | 3- Completed
S5 | S5 | US-001 | Frontend development | MUST HAVE | Vite , React TypeScript | Raviteja | 3- Completed
S6 | S6 | US-001 | API integration and real-time data handling | MUST HAVE | Backend APIs | Pravin | 3- Completed
S7 | S7 | US-001 | Testing and debugging of system | SHOULD HAVE | Integration Testing | Harshitha | 3- Completed
S8 | S8 | US-001 | Final deployment, optimization and documentation | MUST HAVE | Render & Vercel | Janani | 3- Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 70 | 18 | 12 | 9 | 7 | 7 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction to project(Form Filling AI) | 2026-02-02 | 2026-02-04 | Janani | Others | 3- Completed | 10 | 2 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Workflow Creation and Project Goal Documentation | 2026-02-05 | 2026-02-07 | Kranthi | Design | 3- Completed | 10 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Document Discussion(Agile Template,Defect Tracker,Unit Testing) | 2026-02-08 | 2026-02-08 | Pravin | Others | 3- Completed | 8 | 0 | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Learn stock market basics | 2026-02-09 | 2026-02-15 | Kranthi | Others | 3- Completed | 6 | 0 | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Fetch stock data using API | 2026-02-16 | 22/Feb/16 | Raviteja | Coding | 3- Completed | 3 | 2 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Implement RSI strategy | 2026-02-23 | 2026-03-01 | Vaishnavi | Regression Test | 3- Completed | 3 | 4 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Build backend using Flask | 2026-03-03 | 2026-03-15 | Pravin | Coding | 3- Completed | 10 | 3 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Deploy project | 2026-03-16 | 22-03-2026 | Janani | System Test | 3- Completed | 10 | 3 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day1 | Difficulty in backend setup (Flask errors) | Referred tutorials and fixed setup
S2 | Day 8 | API integration issues | Tested endpoints and corrected parameters
S3 | Day 15 | UI alignment issues | Adjusted CSS and layout
S4 | Day 22 | Data not displaying in frontend | Fixed API response handling
S5 | Day 29 | Deployment errors in Render | Checked logs and updated config
S6 | Day 36 | Environment variables not working | Configured .env properly
S7 | Day 43 | Final testing bugs | Performed debugging and fixes
S8 | Day 55 | Performance issues | Optimized code and reduced load time

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2026-02-02 | 2026-10-02 | Pravin ,janani,kranthi,Raviteja, Vaishnavi,Harshitha | Learning stock market basics | Random coding without understanding | Research and practice | Understood project flow
2 | S2 | 2026-10-02 | 22-02-2026 | Kranthi | Implementing RSI | Ignoring errors | Debugging | Generated Signals
3 | S3 | 24-02-2026 | 06-03-2026 | Pravin | Backtesting strategy logic | Hardcoding without documentation | Code optimization and documentation | Completed backtesting
5 | S5 | 12-03-2026 | 20-03-2026 | Pravin | Integrating API data | Delaying implementation | Coding consistency | Fetched real-time stock data
6 | S6 | 20-03-2026 | 24-03-2026 | Raviteja | Building frontend UI | Ignoring UI design | Testing features | Created basic dashboard
7 | S7 | 24-03-2026 | 28-03-2026 | Raviteja | Improving UI/UX | Hardcoding values | Debugging | Enhanced user experience
8 | S8 | 28-03-2026 | 31-03-2026 | Janani | Final deployment | Last-minute changes | Documentation | Successfully deployed project